## Questions
Ref. | Area | Required Clarification / Question | Impact / Required Confir-mation | Customer Answer
Q1 | NEXT3 Sand-box Availabil-ity | When can the NEXT3 sandbox environment be made available? The required information should include the environment URL, access cre-dentials, authentication mechanism (OAuth, API key, mutual TLS, or other supported method), applicable API/rate limits, and representative test data. | Early availability of the non prod sandbox will allow the devel-opment team to move from simulated NEXT3 interfaces to actual integration development and testing. The ex-pected availability date should therefore be con-firmed as part of project ini-tiation. | The api concept is already found but there is a change on authentication level that we need to check
Q2 | Integration & Connectivity Method | Please confirm the integration mechanism supported by NEXT3. Will integration be performed through web APIs, or through a shared directory for file/document transfer combined with database record insertion? If direct database integration is required, please also confirm the database technology/platform used by NEXT3 and the applicable connectivity require-ments. | The two approaches require different integration architectures and development activities. Early confirmation is required to finalize the tech-nical design, connectivity requirements, security configuration, and implementation approach while avoiding un-necessary rework. | API call
Q3 | Duplicate Pre-vention / Idem-potency | Does NEXT3 support a unique ref-erence identifier supplied by the calling application when submitting documents or photographs? If the same reference is submitted again, can NEXT3 recognize the previous transaction and reject or ignore the duplicate submission? | This is required to ensure data integrity during retries. If NEXT3 receives a file but the confirmation is interrupted, the application should be able to safely retry without creating a duplicate document in the claim file. | in the current system when trying to upload the same image NEXT3 is giving that the file is already received
Q4 | New Claim As-signment Noti-fication | How will the application be in-formed when a new visa/claim is assigned to an expert? The preferred approach is for NEXT3 to send an event or notification to the application. If this capability is not available, please confirm whether the application should periodically query NEXT3 for new assignments. | This mechanism initiates the expert workflow and allows the application to notify the expert when a new claim is assigned. If polling is required, the polling frequency and relevant API limitations will also need to be agreed. | Option1 : We can give the application an access to an oracle database and perform a specific query to retrieve the recent created claims identified by a visa no or notification_id. To have the possibility in the application to set Database connection (Username, password, Hostname, Port, Service name) (The query call can be done every 15 seconds to be executed) | Option2 : Add a connection in oracle database to mobile application database or any middleware and on table insert in NEXT3 a trigger will execute the insert in the middleware/mobileapp database (not recommended) | `
Q5 | Expert-to-Claim Assign-ment & Access Control | How does NEXT3 identify the relationship between an expert and the claims assigned to them? Please confirm the relevant field/relation-ship and whether this information is returned through the claim and search interfaces. | The assignment information is required to enforce claim-level access control. The ap-plication must ensure that an expert can only access and search claims assigned to them. Since NEXT3 owns the assignment relationship, this linkage must be availa-ble through the integration. | similar to Q4 a query will be provided to read those data find attached example of query UAT NEXT3 GET VISA.sql
Q6 | Expert Arrival Information | For the “Expert Arrived” action, please confirm the exact fields that NEXT3 expects the application to update, the interface/endpoint through which they should be sub-mitted, and the required formats for date, time, and GPS coordinates. | Confirmation is required to ensure that the arrival infor-mation captured by the appli-cation is correctly structured and recorded against the cor-responding NEXT3 claim without relying on assumptions. | The update is to be done as follow in table CARS_LOSS_TOWING fields DISTRIBUTION_LOSS_ARRIVED (Y/N), DISTRIBUTION_LOSS_ARRIVED_DATE (Date) where NOTIFICATION_ID=the one in mobile application
Q7 | User Master Data | Please confirm how the master data for experts, garages and claim officers will be provided, including the format and whether it will be supplied as an initial extract only or synchronized periodically. If brokers also have a NEXT3 identity, their records should be included; otherwise, the source of the applicable IRIS code list should be confirmed. | This information is required during user onboarding and synchronization to ensure that every application user can be correctly associated with their corresponding NEXT3 record and identifier. | Expert and Garage list to be read from NEXT3 live using a query with specific columns taking into consideration the below : * if new record and OUT NETWORK='N' then to be created in app + push a notification to phone number to register * if existing record and not showing anymore in query then to block the user from entering his code until it is received again * sync on this level can be done once per day | Claim officers & Brokers to be created on the mobile application with the possibility to set from our side an ID (char) used following the existing code in our core system, TO CHECK THE NEW BRD SHARED WHERE SOME CHANGES ARE ADDED ON CLAIM OFFICER
Q8 | Voice Notes / Audio Files | Please confirm whether NEXT3 supports the storage of audio files/voice notes, including the supported file formats, maximum file size, and the NEXT3 document type/category under which the audio should be stored. | The application requirements include the ability for experts to record voice notes. If NEXT3 cannot accept audio files, an alternative storage or processing approach will need to be agreed with AXA. | The files are stored in the server directory and not on database level as a file and supports audio and images files
Q9 | Photograph Re-quirements | Please confirm NEXT3's rules and limitations for claim photographs, including the maximum number of photographs per claim/folder, maxi-mum individual file size, accepted formats, and any image resolution restrictions. In addition, please confirm whether AXA requires any au-tomated image tampering or fraud-detection capability. | These requirements will determine the design and con-figuration of the image cap-ture and upload process. Automated fraud or tampering detection is not included in the current scope and, if required, would need to be assessed and scoped separately. | There is no specific limitation and no specific file format (jpg,png, mp4,..), to include the feature as a standalone feature with pricing and based on impact AXA to decide
Q10 | Vehicle Dam-age Identifica-tion | Does AXA have an existing standard vehicle damage diagram, damage classification, or predefined set of damage codes that should be incorporated into the application, or can the proposed application use a free-form vehicle damage-marking approach? | Confirmation will determine the design of the vehicle damage capture interface and whether it needs to comply with an existing AXA dam-age-assessment standard or coding structure. | We don’t have a standard form, but mainly the use is identify which sides the damages are found, can be a simple diagram which the expert and the garage can check it
Q11 | Creation of Missing Visa / Claim | When a claim officer searches for a visa that does not yet exist in NEXT3, should the visa/claim be created directly in NEXT3 by the claim officer, after which the appli-cation performs another lookup, or is the proposed application ex-pected to provide functionality to create the record in NEXT3? | Confirmation is required to clearly define system responsibilities and avoid implementing unnecessary claim-creation functionality within the application if NEXT3 remains responsible for creating the initial visa/claim record. | The search of visa should be done using the query provided "UAT NEXT3 GET VISA to be used with search.sql" when the claim officer don’t find a visa relared to GARAGE declaration, the claim officer will access next3 and create the visa, then try to search the visa in mobile application using the same query no visa creation is required in mobile application
Q12 | Mobile & PC Functionality | Please confirm whether the mobile and PC/browser versions of the application are expected to provide the same features or whether the proposed role-based split is acceptable. The proposed approach is one application and one login accessible from either device, with mobile devices used for field activities requiring direct camera capture. Experts and Garages would primarily operate through mobile devices, while Claim Officers and Brokers would mainly use the browser/PC interface. This is particularly relevant because the BRD requires vehicle photographs to be captured di-rectly rather than uploaded from an existing file. | The proposed approach maintains a single code-base while aligning func-tionality with the practical needs of each user role. Full feature parity across mobile and PC would require allowing photograph uploads from a PC, which would conflict with the BRD's capture-only requirement. This should therefore be confirmed before development of the relevant functionality. | BRD's capture-only requirement should be optional per profile where AXA can change to allow specific expert/garage/broker to upload car photos for any exceptions found along with the application use
Q13 | Offline Cap-ture | Offline capture is not included in the current phase, and the application is expected to have an active data connection when information, photographs, or documents are submitted. Please confirm whether AXA requires users to be able to capture and temporarily store information while offline and synchronize it once connectivity becomes available. | Offline functionality is not included, If required, it would need to be incorporated into the solution design. | not necessary to have offline mode, however please to provide the estimation separately
Q14 | Image & Voice Clarity Valida-tion | Please confirm whether the proposed approach for validating image visibility and voice clarity satisfies AXA's requirement. The application will perform practical checks on photographs at the time of capture, including resolution and sharpness, and will immediately warn the user and offer a retake where an image is too small, too dark, or blurred. Voice notes will be confirmed through playback before submission. These checks validate technical quality but do not determine whether the correct subject or damaged vehicle has been captured. | The current approach includes the listed device-level technical quality checks. Reviewer-based manual validation, including re-view and rejection work-flows, and automated as-sessment of image content using machine-learning techniques are not in-cluded in the current scope and would require separate assessment, scoping, and quotation if requested by AXA. | confirmed
Q15 | Expected Usage Volumes | Please confirm the expected operational volumes for the application. In the absence of confirmed figures in the BRD, the current sizing and host-ing-cost estimate assumes approxi-mately 100 claims per day (around 3,000 claims per month), an average of 15 photographs per claim at ap-proximately 1.5 MB per photograph, and approximately 200 users across all four user profiles. Please confirm whether these assumptions are repre-sentative of the expected production volumes and, if not, provide the expected number of claims per day/month, average photographs per claim, average photograph size, and expected number of users. | These volumes are key inputs to infrastructure sizing and the estimated Azure hosting cost. Higher or lower transaction vol-umes, image volumes, storage requirements, and user concur-rency may affect compute, da-tabase, storage, monitoring, and data-transfer consumption. Confirmed volumes will there-fore allow the hosting estimate to be refined more accurately. | Over the past 200 days, we observed an average of 15 claims per day, with a maximum of 32 claims recorded in a single day. Regarding photo sizes, it is advisable to adopt a standardized approach by configuring the applicatio to save images within an acceptable size limit. as for users to be increased since it will be covering experts, garage and brokers
Q16 | Application Envi-ronments | Please confirm whether AXA requires one application environment or two environments. The options considered are: (1) a single Production environ-ment; or (2) separate Test/UAT and Production environments. The recom-mended approach is to maintain a separate Test/UAT environment alongside Production so that fixes, up-grades, configuration changes, and new releases can be validated and approved before being deployed to the live environment. | The number of environments directly affects the hosting architecture and recurring Azure cost. A second environment will require additional application, database, monitoring, and related cloud resources and may therefore approximately increase the infrastructure cost compared with a single Pro-duction environment. It also aligns naturally with having a NEXT3 sandbox for non-production integration testing. | confirmed
Q17 | SMS Provider & OTP Authentica-tion | Please confirm the SMS provider to be used for sending one-time login verification codes (OTP) to application users. Please also confirm whether AXA already has an approved corporate SMS provider/account that should be used or whether a new account should be established in AXA's name. Where an existing provider is available, the relevant API documentation, credentials/access mechanism, supported countries, and applicable sending restrictions should be provided. | Pricing varies by provider, destination country, and message volume. Confirmation of the selected provider and expected SMS volumes is required to determine the applicable messaging cost and complete the authentication integration. | Is there any possibility of sending the otp using whatsapp noting that this process will be only needed on the registration of new member on the application. As for sms provider we have one but we need to check if it is still active
Q18 | Mobile Applica-tion Distribution | Please confirm how AXA intends to distribute the mobile application. Should the application be published through the public Apple App Store and Google Play Store, or distributed internally through AXA's enter-prise/mobile device management environment? If public app-store distribution is required, please confirm whether AXA already maintains Apple Developer Program and Google Play developer accounts. These accounts should be held in AXA's name as the application will be published under AXA's identity. | The selected distribution method affects both setup activities and external account costs. If AXA uses its own internal device-management distribution, these public app-store registration requirements and associated re-view cycles can be avoided. | needs more clarificatrion on this topic

## Sheet1
TO_CHAR(T.SYS_CREATED_DATE,'YYYY/MM/DD') | COUNT(*)
2026-08-07 | 13
2026-02-25 | 23
2026-06-10 | 23
2026-06-20 | 11
2026-06-02 | 24
2026-05-25 | 16
2026-08-05 | 31
2026-03-25 | 11
2026-04-29 | 14
2026-06-27 | 6
2026-07-26 | 4
2026-07-08 | 17
2026-04-01 | 11
2026-02-24 | 25
2026-02-28 | 13
2026-05-17 | 9
2026-03-08 | 3
2026-04-26 | 7
2026-05-31 | 4
2026-08-22 | 9
2026-03-29 | 5
2026-08-02 | 4
2026-07-25 | 2
2026-04-21 | 20
2026-07-19 | 1
2026-04-30 | 18
2026-07-13 | 30
2026-03-06 | 15
2026-03-26 | 21
2026-07-22 | 32
2026-07-01 | 19
2026-02-10 | 21
2026-08-21 | 20
2026-05-06 | 21
2026-02-18 | 19
2026-05-18 | 17
2026-05-26 | 21
2026-08-12 | 20
2026-06-28 | 4
2026-05-16 | 9
2026-05-28 | 6
2026-03-04 | 12
2026-04-25 | 5
2026-08-23 | 5
2026-02-21 | 8
2026-03-22 | 2
2026-03-19 | 16
2026-08-04 | 6
2026-07-21 | 15
2026-04-20 | 16
2026-07-10 | 22
2026-04-07 | 24
2026-05-01 | 8
2026-04-27 | 26
2026-02-26 | 24
2026-08-17 | 20
2026-08-13 | 22
2026-08-11 | 15
2026-04-06 | 9
2026-04-14 | 21
2026-08-18 | 32
2026-04-22 | 14
2026-06-25 | 10
2026-02-11 | 16
2026-03-14 | 12
2026-04-24 | 14
2026-08-01 | 12
2026-04-10 | 8
2026-04-19 | 5
2026-02-27 | 12
2026-06-06 | 6
2026-06-19 | 13
2026-05-02 | 2
2026-08-16 | 2
2026-05-10 | 3
2026-03-01 | 2
2026-06-01 | 19
2026-04-09 | 9
2026-08-14 | 14
2026-03-09 | 16
2026-03-24 | 29
2026-06-29 | 23
2026-03-11 | 26
2026-06-03 | 20
2026-07-14 | 23
2026-07-24 | 14
2026-03-17 | 16
2026-05-20 | 16
2026-03-16 | 25
2026-05-04 | 22
2026-06-18 | 19
2026-02-15 | 7
2026-07-07 | 26
2026-06-04 | 16
2026-04-28 | 16
2026-07-12 | 6
2026-06-30 | 20
2026-03-27 | 17
2026-05-27 | 5
2026-02-17 | 19
2026-02-08 | 4
2026-05-23 | 10
2026-08-15 | 5
2026-04-12 | 2
2026-03-02 | 17
2026-04-16 | 14
2026-06-16 | 10
2026-06-17 | 23
2026-03-20 | 9
2026-05-12 | 21
2026-06-12 | 18
2026-07-28 | 23
2026-06-09 | 25
2026-06-26 | 8
2026-02-16 | 26
2026-03-13 | 23
2026-02-13 | 22
2026-05-13 | 19
2026-05-21 | 17
2026-04-18 | 7
2026-03-10 | 27
2026-05-08 | 12
2026-03-07 | 8
2026-08-25 | 11
2026-03-03 | 12
2026-07-31 | 16
2026-05-30 | 5
2026-06-07 | 2
2026-02-22 | 4
2026-07-16 | 22
2026-05-05 | 17
2026-02-20 | 26
2026-02-19 | 18
2026-07-27 | 25
2026-05-22 | 26
2026-04-03 | 8
2026-03-31 | 14
2026-07-30 | 20
2026-07-17 | 20
2026-07-18 | 4
2026-06-11 | 25
2026-04-13 | 9
2026-06-23 | 20
2026-06-21 | 5
2026-07-11 | 11
2026-05-09 | 9
2026-03-28 | 8
2026-05-29 | 13
2026-06-22 | 18
2026-07-02 | 22
2026-03-12 | 14
2026-06-24 | 15
2026-02-09 | 9
2026-07-03 | 11
2026-03-15 | 6
2026-04-05 | 6
2026-08-09 | 3
2026-06-14 | 1
2026-03-30 | 29
2026-08-19 | 25
2026-02-23 | 22
2026-08-24 | 28
2026-05-19 | 14
2026-04-08 | 14
2026-07-20 | 20
2026-07-15 | 19
2026-08-06 | 28
2026-06-13 | 8
2026-07-04 | 6
2026-05-03 | 7
2026-08-20 | 29
2026-06-08 | 18
2026-04-17 | 18
2026-06-15 | 18
2026-03-05 | 11
2026-07-23 | 15
2026-08-27 | 3
2026-04-04 | 6
2026-08-08 | 11
2026-07-29 | 18
2026-05-11 | 16
2026-08-03 | 20
2026-02-12 | 22
2026-03-18 | 18
2026-03-21 | 8
2026-06-05 | 19
2026-05-14 | 18
2026-07-06 | 14
2026-05-07 | 9
2026-04-23 | 22
2026-05-15 | 23
2026-08-10 | 26
2026-04-15 | 15
2026-04-02 | 23
2026-08-26 | 25
2026-05-24 | 4
2026-02-14 | 9
2026-07-09 | 20
2026-04-11 | 6
2026-03-23 | 13
2026-07-05 | 1