COMMERCIAL PROPOSAL

Motor Claim Management Application

A single mobile-and-web system that links every photo, document and decision on a motor claim to its NEXT3 visa number automatically — replacing the manual email process between experts, garages, claim officers and brokers.

# 01  Assumptions

What this proposal is priced and scheduled against. Any change to these is a change to the number in section 07, not a renegotiation of it.

Claim volume: client-measured over 200 real days — average 15 claims/day, peak 32 in a single day. Well below early planning assumptions; hosting is sized to this.

Users: roughly 200 accounts across the four roles at launch, expected to grow once experts, garages and brokers are fully onboarded — no firm ceiling given yet.

NEXT3 integration is API-only — confirmed by the client. No direct database access into NEXT3 is required or built.

NEXT3 is the system of record for photos and documents. This application holds files only in transit — days, not indefinitely — and is not a long-term archive.

All third-party costs run on AXA's own accounts — Azure subscription, SMS gateway, domain — billed directly to AXA, not passed through this engagement.

Single tenant, English only. No multi-client isolation, no Arabic/RTL/French layout.

Timeline starts on delivery of the dependencies below — sandbox access, an Azure subscription, and an answer on whether an AXA Group InfoSec review applies. A delay to any of these moves the date by the same number of days; it is not absorbed silently.

# 02  Scope limits

Everything in the BRD that is deliberately not in this price. Each is available as separately quoted work.

| Excluded | Why |
| --- | --- |
| Offline mode | Not in the BRD; genuinely useful roadside. Recommended as a phase 2. |
| Arabic / RTL, French | A second layout, not a translation pass. |
| 24/7 support & production SLA | Replaced by a defined hypercare window — see section 06. |
| Reporting, MIS, dashboards | Not requested in the BRD. |
| Voice transcription | Voice notes are recorded, stored and played back — not transcribed. |
| In-app visa creation | Where no visa exists, the claim officer creates it in NEXT3 directly. |

# 03  Delivery plan

Eight weeks from kickoff (see section 01's dependency clause). Two checkpoints anchor the schedule: a working demo in week 4, and UAT in week 8.

| Week | Work |
| --- | --- |
| 1 | Repo, phone-OTP login, admin onboarding for all four roles, NEXT3 client built behind a swappable interface so nothing blocks on their API being ready |
| 2 | Expert: claim list, claim detail, Arrived-to-NEXT3, photo capture with the clarity check, four document buckets |
| 3 | Expert: voice note, damage diagram, search, report upload; NEXT3 sandbox swap-in when access is granted |
| 4 | Garage declaration + Claim Officer review/approve/reject — CLIENT DEMO |
| 5 | Repair uploads, rejection handling, Broker Option 1 + email routing, Broker Option 2 public form |
| 6 | Broker Option 2 photo capture, mobile app wrapper, real-device checkpoint |
| 7 | Security hardening on the public-facing broker link, audit log, error states, UAT preparation |
| 8 | UAT — ONE ROUND, deploy, handover documentation, training |

# 04  Environments

Two environments, as agreed with AXA: a UAT/test environment for demos and pre-release validation, and production for live claims. Both run in AXA's own Azure subscription and are billed to AXA directly — not part of the fixed price below.

UAT / Test — scale-to-zero.

Spins down to near-zero cost when idle between demos and test cycles; NEXT3 runs against a realistic fake until the real sandbox is connected, so testing is never blocked by AXA's side being unavailable.

Production — always warm.

Kept warm at all times — no cold-start delay for an expert opening a claim popup at an accident scene. Connects to the real NEXT3 system once credentials are provided.

| Component | UAT | Production |
| --- | --- | --- |
| Application hosting (Container Apps) | $0 – 5 | $20 – 50 |
| Background retry worker | $0 – 2 | $3 – 7 |
| Database (Azure SQL, serverless vCore, auto-pause on UAT)* | $3 – 10 | $25 – 50 |
| File storage (transit only, days not permanent) | ~$0.25 – 1 | ~$0.25 – 1 |
| Container registry & monitoring | shared | $5 – 15 |
| WhatsApp/SMS one-time codes | nominal | $10 – 30 |
| Combined estimate |  | ≈ $75 – 150 / month |

* Serverless (vCore-based), not the DTU-based S-tier — auto-pauses on UAT so it bills only active compute; production sizing finalized once real query patterns are measured.

† Native Azure Communication Services SMS does not reach Lebanon directly and needs a regional gateway (e.g. an Infobip-via-ACS connector, or a direct MENA aggregator such as Unifonic) — the routing choice, not the dollar estimate, is what needs deciding.

Estimate at current confirmed claim volumes; refined once the environments are actually provisioned. A managed web-application firewall (~$330/month) is available if AXA Group InfoSec mandates one for the public broker-link surface — not included by default.

# 06  Support

Go-live hypercare  (Included)

3 Month, business hours, immediately after handover. Covers defects against the agreed scope only — not new requirements, which are quoted separately.

Ongoing support beyond hypercare  (Quoted separately)

Not included in the fixed price. Billed as 2000$/year for full support.

# 07  Commercial summary

Fixed price for the scope defined in sections 01–02, delivered on the schedule in section 03. Hosting (section 04) is billed separately, directly to AXA's own Azure subscription.

| Fixed price · full scope · 8 weeks | $5,000 |
| --- | --- |

Payable 30% at the week-4 demonstration, balance on delivery and UAT sign-off in week 8.

(Payment split shown reflects the existing week-4 demo milestone; confirm this exact split with the client before sending.)

Motor Claim Management Application — Commercial Proposal		AXA Middle East · OZ-Consultancy